## Basic Manual Gantt Chart
Task Name | Start Date | End Date | Duration | Name
Design UI | 2017-01-26 | 2017-02-01 | 6
Create a Project in Firebase | 2017-01-26 | 2017-01-28 | 2
Rehearsal for initial presentation | 2017-02-06 | 2017-02-07 | 1
Initial report and presentation | 2017-01-26 | 2017-02-07 | 12
iOS | 2017-01-28 | 2017-03-07 | 38 | Fernando, Remi, Khalid
iOS Link Xcode to Firebase | 2017-01-28 | 2017-01-30 | 2
iOS link Xcide to Github | 2017-01-28 | 2017-01-30 | 2
iOS Download Firebase files to the project directory | 2017-01-28 | 2017-02-01 | 4
iOS Build the login page | 2017-02-01 | 2017-02-03 | 2
iOS Install SDK for Cocoapods | 2017-02-03 | 2017-02-05 | 2
iOS Login with email and password (and Gmail if possible) | 2017-02-05 | 2017-02-07 | 2
iOS Fetch users from database | 2017-02-05 | 2017-02-11 | 6
iOS Upload images to Firebase | 2017-02-11 | 2017-02-13 | 2
iOS Load images from Firebase | 2017-02-13 | 2017-02-15 | 2
iOS Send messages | 2017-02-15 | 2017-02-17 | 2
iOS Load messages | 2017-02-17 | 2017-02-19 | 2
iOS Encryption | 2017-02-19 | 2017-02-23 | 4
iOS Create chat bubbles | 2017-02-19 | 2017-02-21 | 2
iOS Add keyboard | 2017-02-21 | 2017-02-23 | 2
iOS Send images | 2017-02-23 | 2017-02-25 | 2
iOS Load images | 2017-02-25 | 2017-02-27 | 2
iOS Chat log | 2017-02-27 | 2017-03-01 | 2
iOS Revision and Testing | 2017-03-01 | 2017-03-05 | 4
Android | 2017-01-28 | 2017-03-07 | 38 | Santiago, Mariye, Nico
Android Link Android Studio to Firebase | 2017-01-28 | 2017-01-30 | 2
Android Link Android Studio to Github | 2017-01-28 | 2017-01-30 | 2
Android Download Firebase files to the project directory | 2017-01-28 | 2017-02-01 | 4
Android Implement the design | 2017-02-01 | 2017-02-03 | 2
Android Build the login page | 2017-02-03 | 2017-02-05 | 2
Android Login with email and password (and Gmail if possible) | 2017-02-05 | 2017-02-07 | 2
Android Fetch users from database | 2017-02-05 | 2017-02-11 | 6
Android Upload images to Firebase | 2017-02-11 | 2017-02-13 | 2
Android Load images from Firebase | 2017-02-13 | 2017-02-15 | 2
Android Send messages | 2017-02-15 | 2017-02-17 | 2
Android Load messages | 2017-02-17 | 2017-02-19 | 2
Android Create chat bubbles | 2017-02-19 | 2017-02-21 | 2
Android Add keyboard | 2017-02-21 | 2017-02-23 | 2
Android Send images | 2017-02-23 | 2017-02-25 | 2
Android Load images | 2017-02-25 | 2017-02-27 | 2
Android encryption | 2017-02-27 | 2017-03-03 | 4
Android Chat log | 2017-02-27 | 2017-03-01 | 2
Android Revision and Testing | 2017-03-01 | 2017-03-05 | 4
Implementing new features | 2017-03-05 | 2017-03-19 | 14
Debugging | 2017-03-05 | 2017-03-25 | 20
Final rehearsal | 2017-03-25 | 2017-03-26 | 1
Final report and presentation | 2017-02-07 | 2017-03-29 | 50
Formulas:
End Date = [Start Date]+6
End Date = [End Date, row below]
Start Date = [End Date, row below]-1
Start Date = [Start Date, row below]

## Gantt Chart - Manual End Date
Task Name | Start Date | End Date | Duration (Days) | Days Complete | Days Remaining | Percent Complete | Start Date in Number Form | 42576 | Use this number for the Minimum Bound of the Horizontal Axis to set the beginning of the chart.
Task One | 2016-07-25 | 2016-07-30 | 5 | 2.5 | 2.5 | 50%
Task Two | 2016-07-27 | 2016-08-01 | 5 | 3.75 | 1.25 | 75%
Task Three | 2016-07-27 | 2016-08-04 | 8 | 2 | 6 | 25%
Task Four | 2016-07-29 | 2016-08-06 | 8 | 8 | 0 | 100%
Task Five | 2016-08-01 | 2016-08-09 | 8 | 6 | 2 | 75%
Task Six | 2016-08-01 | 2016-08-05 | 4 | 1.4 | 2.6 | 35%
Task Seven | 2016-08-03 | 2016-08-10 | 7 | 1.75 | 5.25 | 25%
Task Eight | 2016-08-05 | 2016-08-12 | 7 | 4.9 | 2.1 | 70%
Task Nine | 2016-08-03 | 2016-08-09 | 6 | 0.9 | 5.1 | 15%
Task Ten | 2016-08-06 | 2016-08-10 | 4 | 2.4 | 1.6 | 60%
Task Eleven | 2016-08-07 | 2016-08-13 | 6 | 3.9 | 2.1 | 65%
Task Twelve | 2016-08-10 | 2016-08-16 | 6 | 1.5 | 4.5 | 25%
Task Thirteen | 2016-08-14 | 2016-08-19 | 5 | 1.5 | 3.5 | 30%
Task Fourteen | 2016-08-15 | 2016-08-23 | 8 | 4 | 4 | 50%
Task Fifteen | 2016-08-16 | 2016-08-26 | 10 | 4 | 6 | 40%
Task Sixteen | 2016-08-17 | 2016-08-28 | 11 | 3.85 | 7.15 | 35%
Task Seventeen | 2016-08-18 | 2016-08-29 | 11 | 1.65 | 9.35 | 15%
[7 empty] | Key: | Calculated Cell |  | Manual Entry Cell
[8 empty] | These cells will be automatically calculated based on the inputs on other cells. |  | These cells require manual input so the calculated cells have data to work with.

## Gantt Chart - Manual Duration
Task Name | Start Date | End Date | Duration (Days) | Days Complete | Days Remaining | Percent Complete | Start Date in Number Form | 42576 | Use this number for the Minimum Bound of the Horizontal Axis to set the beginning of the chart.
Task One | 2016-07-25 | 2016-07-30 | 5 | 2.5 | 2.5 | 50%
Task Two | 2016-07-27 | 2016-08-01 | 5 | 3.75 | 1.25 | 75%
Task Three | 2016-07-27 | 2016-08-04 | 8 | 2 | 6 | 25%
Task Four | 2016-07-29 | 2016-08-06 | 8 | 8 | 0 | 100%
Task Five | 2016-08-01 | 2016-08-09 | 8 | 6 | 2 | 75%
Task Six | 2016-08-01 | 2016-08-05 | 4 | 1.4 | 2.6 | 35%
Task Seven | 2016-08-03 | 2016-08-10 | 7 | 1.75 | 5.25 | 25%
Task Eight | 2016-08-05 | 2016-08-12 | 7 | 4.9 | 2.1 | 70%
Task Nine | 2016-08-03 | 2016-08-09 | 6 | 0.9 | 5.1 | 15%
Task Ten | 2016-08-06 | 2016-08-10 | 4 | 2.4 | 1.6 | 60%
Task Eleven | 2016-08-07 | 2016-08-13 | 6 | 3.9 | 2.1 | 65%
Task Twelve | 2016-08-10 | 2016-08-16 | 6 | 1.5 | 4.5 | 25%
Task Thirteen | 2016-08-14 | 2016-08-19 | 5 | 1.5 | 3.5 | 30%
Task Fourteen | 2016-08-15 | 2016-08-23 | 8 | 4 | 4 | 50%
Task Fifteen | 2016-08-16 | 2016-08-26 | 10 | 4 | 6 | 40%
Task Sixteen | 2016-08-17 | 2016-08-28 | 11 | 3.85 | 7.15 | 35%
Task Seventeen | 2016-08-18 | 2016-08-29 | 11 | 1.65 | 9.35 | 15%
[7 empty] | Key: | Calculated Cell |  | Manual Entry Cell
[8 empty] | These cells will be automatically calculated based on the inputs on other cells. |  | These cells require manual input so the calculated cells have data to work with.